## HTML Mapping
Sheet/Tab Name | Section | HTML ID | HTML Class | HTML Parent Structure | Description
Overview | Workshop Overview | #overview > .card > .overview-grid > .kpi-card | kpi-card | .card > .overview-grid | 3 Planning Days
Overview | Workshop Overview | #overview > .card > .overview-grid > .kpi-card | kpi-card | .card > .overview-grid | 11 Topics
Overview | Workshop Overview | #overview > .card > .overview-grid > .kpi-card | kpi-card | .card > .overview-grid | Sep 15 2026 Dreamforce Target
Overview | Workshop Overview | #overview > .card > .overview-grid > .kpi-card | kpi-card | .card > .overview-grid | 76 Days to Dreamforce
Overview | Key Topics | #overview > .card | product-tag tag-s360/tag-sc/tag-prom | .card | Headless Experience
Overview | Key Topics | #overview > .card | product-tag tag-s360 | .card | In-App Experience
Overview | Key Topics | #overview > .card | product-tag tag-s360/tag-sc/tag-prom | .card | ProM & Scale Center Migration to Scale360 & EOL
Overview | Key Topics | #overview > .card | product-tag tag-s360 | .card | Basic & Elite Scale360 Product
Overview | Key Topics | #overview > .card | product-tag tag-s360 | .card | Internal Support / CSM
Overview | Key Topics | #overview > .card | product-tag tag-s360 | .card | Product Launch to GA
Overview | Key Topics | #overview > .card | product-tag tag-s360 | .card | Pricing & CTS Opt-In AI-Based
Overview | Key Topics | #overview > .card | product-tag tag-s360 | .card | RCA Agent
Overview | Key Topics | #overview > .card | product-tag tag-s360 | .card | Alerting & Alert Enrichment
Overview | Key Topics | #overview > .card | product-tag tag-s360 | .card | Multi-Org & Multi-Cloud
Overview | Key Topics | #overview > .card | product-tag tag-s360 | .card | Architecture Comparison
Overview | Key Topics | #overview > .card | product-tag tag-s360 | .card | UX Session
Overview | 3-Day Structure | #overview > .card |  | .card | Day 1 — User Journey Headless Experience (7.25 hrs)
Overview | 3-Day Structure | #overview > .card |  | .card | Day 2 — UX/Product Launch to GA (7.5 hrs)
Overview | 3-Day Structure | #overview > .card |  | .card | Day 3 — Elevator Pitch & Key Decisions (4.75 hrs)
Overview | R266 Key Dates | #overview > .card |  | .card | Aug 3–7 (TBD)
Overview | R266 Key Dates | #overview > .card |  | .card | Aug 20
Overview | R266 Key Dates | #overview > .card |  | .card | Sep 15
Overview | R266 Key Dates | #overview > .card |  | .card | Nov 19
Overview | R266 Key Dates | #overview > .card |  | .card | Dec 10
Overview | R266 Key Dates | #overview > .card |  | .card | Jan 31 2027
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Welcome & Planning Kickoff
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Future State User Journey
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 1 — Headless Experience
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row break-row | .card-body > .session-row | ☕ BREAK
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 1.1 — In-App Experience
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 3 — Basic & Elite Scale360 Product
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row break-row | .card-body > .session-row | 🍽 LUNCH
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 8 — Alerting & Alert Enrichment
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row break-row | .card-body > .session-row | ☕ BREAK
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 7 — RCA Agent
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 9 — Multi-Org & Multi-Cloud
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Day 1 Recap & Action Items
Day 1 | Schedule | #day1 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Happy Hour 🍷
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row recap-row has-links | .card-body > .session-row | Day 2 Kickoff
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 11 — UX Session
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 6 — Pricing & CTS Opt-In AI-Based
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row break-row has-links | .card-body > .session-row | ☕ BREAK
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 2 — ProM & Scale Center Migration & EOL
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row break-row has-links | .card-body > .session-row | 🍽 LUNCH
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 4 — Internal Support / CSM
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 5 — Product Launch to GA
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row break-row has-links | .card-body > .session-row | ☕ BREAK
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Topic 10 — Architecture Comparison
Day 2 | Schedule | #day2 > .card > .card-body > .session-row | session-row recap-row has-links | .card-body > .session-row | Day 2 Recap & Action Items
Day 3 | Schedule | #day3 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Day 3 Kickoff
Day 3 | Schedule | #day3 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Breakout - Scale360 Elevator Pitch
Day 3 | Schedule | #day3 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Workshop Outcomes Review & Key Decisions w/ Pending Decision Log
Day 3 | Schedule | #day3 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Workstream Planning & Action Items
Day 3 | Schedule | #day3 > .card > .card-body > .session-row | session-row has-links | .card-body > .session-row | Close & Next Steps
Topics | Topic 1 - Headless Experience | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Headless Experience (Scale360, Scale Center, ProM)
Topics | Topic 1 - Headless Experience | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Headless Experience - Automation & Proactive Delivery
Topics | Topic 1 - Headless Experience | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Headless Experience - MCP Servers & Platform Infrastructure
Topics | Topic 1.1 - In-App Experience | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | In-App Experience (Scale360)
Topics | Topic 2 - ProM & SC Migration & EOL | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | ProM & Scale Center Parity & EOL / Migration to Scale360
Topics | Topic 3 - Basic & Elite Scale360 | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Basic & Elite Scale360 Product
Topics | Topic 4 - Internal Support / CSM | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Internal Support / CSM
Topics | Topic 5 - Product Launch to GA | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Product Launch to GA
Topics | Topic 6 - Pricing & CTS | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Pricing & CTS Opt-In AI-Based - Agentforce vs Claude
Topics | Topic 6 - Pricing & CTS | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Pricing & CTS Opt-In AI-Based - Opt-in Strategy
Topics | Topic 6 - Pricing & CTS | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Pricing & CTS Opt-In AI-Based - Pricing
Topics | Topic 7 - RCA Agent | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | RCA (Root Cause Analysis Agent)
Topics | Topic 8 - Alerting & Enrichment | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Alerting & Alert Enrichment - Enrichment Plan
Topics | Topic 8 - Alerting & Enrichment | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Alerting & Alert Enrichment - Events Platform
Topics | Topic 8 - Alerting & Enrichment | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Alerting & Alert Enrichment - Migration Tools
Topics | Topic 8 - Alerting Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | Alert onboarding seed
Topics | Topic 8 - Alerting Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | Alerting enrichment events platform seed
Topics | Topic 8 - Alerting Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | Warden AI Ops auto-remediation seed
Topics | Topic 8 - Alerting Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | Alert rollout seed
Topics | Topic 9 - Multi-Org | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Multi-Org
Topics | Topic 9 - Multi-Org Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | Multi-org alerting seed
Topics | Topic 9 - Multi-Org Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | Org throttling seed
Topics | Topic 9 - Multi-Org Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | Scale Center multi-org data model seed
Topics | Topic 10 - Multi-Cloud | #topics > .card > .topic-section > table.topic-table | topic-table | .topic-section | Multi-Cloud
Topics | Topic 10 - Multi-Cloud Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | Multi-cloud spike results seed
Topics | Topic 10 - Multi-Cloud Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | G2H parity seed
Topics | Topic 10 - Multi-Cloud Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | 50000 tenant support seed
Topics | Topic 10 - Multi-Cloud Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | UIP Heron seed
Topics | Cross-Cutting Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | 3X productivity seed
Topics | Cross-Cutting Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | Blocker escalation seed
Topics | Cross-Cutting Seeds | #topics > .card > .topic-section > .seeds | seeds | .topic-section | Pre-Work Before India seed
Decision Log | Decisions | #decisions > .card > .decision-row | decision-row | .card | D2: AgentForce vs. Claude AI backend
Decision Log | Decisions | #decisions > .card > .decision-row | decision-row | .card | D3: 264 Pilot Scope Lock
Decision Log | Decisions | #decisions > .card > .decision-row | decision-row | .card | D4: ProM EOL Date
Decision Log | Decisions | #decisions > .card > .decision-row | decision-row | .card | D5: Sprint 9A Hardening Lock
Decision Log | Decisions | #decisions > .card > .decision-row | decision-row | .card | D6: NGA Accuracy Threshold
Decision Log | Decisions | #decisions > .card > .decision-row | decision-row | .card | D7: LLM Token Tracking Scope
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | Finalize PM artifacts and topic owners in release planning doc
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | Demo to Sri and team feedback session
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | Consult Sri for inputs + assign team responsibilities
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | Add topics to feature sections in planning doc
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | Schedule strategy review with Donovan + Karishma before Hyderabad trip
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | Dreamforce, pilot and 264/266 product scope alignment
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | Coordinate with Tara to reserve meeting rooms for 3-day sessions
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | Block Shri calendar for relevant product strategy sessions (Wed + Thu)
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | Finalized agenda published
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | Prepare workshop artifacts — architectural and strategic topic documentation
Pre-Work | Pre-Work Items | #prework > .card > table.prework-table | prework-table | .card | 12-month LRP roadmap document for ProM/Scale Center → Scale360 migration
People & RACI | Attendees | #people > .card > .people-grid > .person-card | person-card | .people-grid | Betty Yip
People & RACI | Attendees | #people > .card > .people-grid > .person-card | person-card | .people-grid | Karishma Lalwani
People & RACI | Attendees | #people > .card > .people-grid > .person-card | person-card | .people-grid | Kent Allison
People & RACI | Attendees | #people > .card > .people-grid > .person-card | person-card | .people-grid | Ravi Raina
People & RACI | Attendees | #people > .card > .people-grid > .person-card | person-card | .people-grid | Samir Damle
People & RACI | Attendees | #people > .card > .people-grid > .person-card | person-card | .people-grid | Laksh Venka
People & RACI | Attendees | #people > .card > .people-grid > .person-card | person-card | .people-grid | Paymon Teyer
People & RACI | Attendees | #people > .card > .people-grid > .person-card | person-card | .people-grid | Laurent Pautet
People & RACI | Attendees | #people > .card > .people-grid > .person-card | person-card | .people-grid | Archana Sethuraman
People & RACI | Attendees | #people > .card > .people-grid > .person-card | person-card | .people-grid | Sriram Dinavahi
People & RACI | RACI Legend | #people > .card |  | .card | R - Responsible
People & RACI | RACI Legend | #people > .card |  | .card | A - Accountable
People & RACI | RACI Legend | #people > .card |  | .card | C - Consulted
People & RACI | RACI Legend | #people > .card |  | .card | I - Informed
People & RACI | Session Ownership | #people > .card > table.prework-table | prework-table | .card | Betty Yip
People & RACI | Session Ownership | #people > .card > table.prework-table | prework-table | .card | Karishma Lalwani
People & RACI | Session Ownership | #people > .card > table.prework-table | prework-table | .card | Kent Allison
People & RACI | Session Ownership | #people > .card > table.prework-table | prework-table | .card | Laurent Pautet
People & RACI | Session Ownership | #people > .card > table.prework-table | prework-table | .card | Paymon Teyer
People & RACI | Session Ownership | #people > .card > table.prework-table | prework-table | .card | Archana Sethuraman
Header Metadata | Event Info | #header | .header | header | Scale360 R266 Strategic Planning - India Offsite
Header Metadata | Event Info | #header | .header | header | Jul 22–24 2026 · Salesforce Hyderabad + Google Meet
Header Metadata | Event Info | #header | .header | header | 8:30 AM – 5:00 PM IST
Header Metadata | Event Info | #header | .header | header | TPM: Betty Yip
Header Metadata | Event Info | #header | .header | header | Agenda and Artifacts deadline: Jul 20 2026
Header Metadata | Event Info | #header | .header | header | Topics deadline: Jul 10 2026

## Overview
Section | Title/Topic | Facilitator/Owner | Description/Goals | Product Tags | Additional Notes
Workshop Overview | 3 Planning Days |  |  |  | KPI stat
Workshop Overview | 11 Topics |  |  |  | KPI stat
Workshop Overview | Sep 15 2026 Dreamforce Target |  |  |  | KPI stat
Workshop Overview | 76 Days to Dreamforce |  |  |  | KPI stat with countdown ID=dfCountdown
Key Topics | Headless Experience | Kent, Ravi | Align on portfolio-wide Headless 360 experience and specific use cases across Scale360, ProM, and Scale Center. MCP and platform infrastructure considerations. | Scale360, Scale Center, ProM | Decision makers: Sri/Karishma/Laksh (pre-reviewed by Karishma)
Key Topics | In-App Experience | Samir | Define which features to automate and deliver proactively to users within the Scale360 product experience. | Scale360
Key Topics | ProM & Scale Center Migration to Scale360 & EOL | Kent, Ravi | Align on 12-month LRP and recommendations for migrating ProM and Scale Center customers to Scale360, including staffing, feature timelines, and EOL dates. | Scale360, Scale Center, ProM | Decision makers: Sri/Laksh (pre-reviewed by Karishma)
Key Topics | Basic & Elite Scale360 Product | Ravi, Kent | Product feature scope to inform product packaging and customer eligibility and review options and recommendations. | Scale360 | Decision makers: Sri/Laksh (pre-reviewed by Karishma)
Key Topics | Internal Support / CSM | Ravi, Kent | Proposal for the Scale360 internal product experience for internal users and CSMs, drawing on Scale Center and ProM learnings. | Scale360 | Decision makers: Sri/Laksh (pre-reviewed by Karishma)
Key Topics | Product Launch to GA | Ravi | Align on committed vs. stretch deliverables. Outline of product launch plan and what it takes to GA a product. Assign engineering work and ownership across multiple work streams (security, legal, etc). | Scale360
Key Topics | Pricing & CTS Opt-In AI-Based | Paymon, Ravi | Decide Agentforce vs. Claude AI backend, CTS rationalization, Pricing (Elite, Signature) and customer experience for customers who have not opted in to Agentforce. | Scale360 | Decision makers: Sri/Karishma/Laksh
Key Topics | RCA Agent | Ravi | Align on pilot exit criteria and engineering work in support of pilot. | Scale360
Key Topics | Alerting & Alert Enrichment | Laurent, Paymon | Discuss enrichment gap between ProM and Scale Center and plan for enrichment for Scale360 leveraging Events Platform. Tools to migrate from current Argus to Events platform. | Scale360
Key Topics | Multi-Org & Multi-Cloud | Paymon, Samir | Review the UI experience shared by Samir. Discuss and decide on the product direction and scope for FY27. | Scale360
Key Topics | Architecture Comparison | Auro, Paymon | Current architecture vs. new architecture comparison. Helpful for migration and EOL discussions. MCP Servers & Platform Infrastructure. | Scale360
Key Topics | UX Session | Samir | UX discussion and planning session. | Scale360 | Dan Donovan (optional), Decision makers: Sri/Karishma/Laksh
3-Day Structure | Day 1 — User Journey Headless Experience (7.25 hrs) |  | 9 sessions + breaks | Scale360 | Tuesday Jul 22 2026
3-Day Structure | Day 2 — UX/Product Launch to GA (7.5 hrs) |  | 7 sessions + breaks | Scale360 | Wednesday Jul 23 2026
3-Day Structure | Day 3 — Elevator Pitch & Key Decisions (4.75 hrs) |  | 5 sessions | Scale360 | Thursday Jul 24 2026
R266 Key Dates | Aug 3–7 (TBD) |  | Release Planning
R266 Key Dates | Aug 20 |  | 2RR Readout - HCC 2 Release Roadmap
R266 Key Dates | Sep 15 |  | Dreamforce
R266 Key Dates | Nov 19 |  | R266 Feature Freeze
R266 Key Dates | Dec 10 |  | R266 Release Freeze → GA
R266 Key Dates | Jan 31 2027 |  | Product GA

## Day 1
Time | Duration | Title/Topic | Facilitator/Owner | Description/Goals | Product Tags | Links/Artifacts
8:30–8:45 AM | 15m | Welcome & Planning Kickoff | Sri, Karishma, Laksh, Betty | Welcome message, purpose and agenda for the next several days. Align on R266 product goals and success criteria. | Scale360 | No artifacts required
8:45-9:45 AM | 1 hr | Future State User Journey | Kent, Ravi |  | Scale360 | No artifacts required
9:45–10:45 AM | 1 hr | Topic 1 — Headless Experience | Kent, Ravi | Align on portfolio-wide Headless 360 experience and specific use cases across Scale360, ProM, and Scale Center. Product scope & prioritized use cases across Headless portfolio (ProM, Scale360, Scale Center) + CATT early feedback — Kent, Mayuresh, Ravi; What to automate for users and what to deliver proactively — Samir | Scale360, Scale Center, ProM | Artifact recommended
10:45–11 AM | 15m | ☕ BREAK
11 AM–12 PM | 1 hr | Topic 1.1 — In-App Experience | Samir | Define which features to automate and deliver proactively to users within the Scale360 product experience. | Scale360 | Artifact recommended
12 PM–1 PM | 1 hr | Topic 3 — Basic & Elite Scale360 Product | Ravi, Kent | Product feature scope to inform product packaging and customer eligibility. Review options and recommendations. | Scale360 | Artifact recommended
1 PM-2 PM | 1 hr | 🍽 LUNCH
2 PM–3 PM | 1 hr | Topic 8 — Alerting & Alert Enrichment | Laurent, Paymon | Discuss enrichment gap between ProM and Scale Center and plan for enrichment for Scale360 leveraging Events Platform. Tools to migrate from current Argus to Events platform. | Scale360, Scale Center, ProM | Artifact recommended
3–3:15 PM | 15m | ☕ BREAK
3:15–4:15 PM | 1 hr | Topic 7 — RCA Agent | Ravi | Align on pilot exit criteria and engineering work in support of pilot. | Scale360 | Artifact recommended
4:15–4:45 PM | 30m | Topic 9 — Multi-Org & Multi-Cloud | Paymon, Samir | Review the UI experience shared by Samir. Discuss and decide on the product direction and scope for FY27. | Scale360 | Artifact recommended
4:45–5:15 PM | 30m | Day 1 Recap & Action Items | Betty | Capture all open items. Assign owners and due dates. Confirm deadlines. Preview Day 2 agenda. | Scale360 | No artifacts required
5:15–6:15 PM | 1 hr | Happy Hour 🍷 | Team | Team bonding and informal discussions. | Scale360 | No artifacts required

## Day 2
Time | Duration | Title/Topic | Facilitator/Owner | Description/Goals | Product Tags | Links/Artifacts
8:30–8:45 AM | 15m | Day 2 Kickoff | Sri, Karishma, Laksh, Betty | Open items from Day 1, priorities for today. | Scale360
8:45–9:45 AM | 1 hr | Topic 11 — UX Session | Samir, Dan Donovan (optional) | UX discussion and planning session. | Scale360 | UX planning doc (Samir)
9:45–10:45 AM | 1 hr | Topic 6 — Pricing & CTS Opt-In AI-Based | Paymon, Ravi | Decide Agentforce vs. Claude AI backend, CTS rationalization, Pricing (Elite, Signature) and customer experience for customers who have not opted in to Agentforce. Sub-topics: (1) Agentforce vs. Claude — Paymon; (2) Opt-in & AI-based customer experience — Ravi; (3) Pricing & CTS for Basic and Elite — Ravi | Scale360 | Pricing & CTS doc (Ravi); Customer opt-in POV (Ravi)
10:45–11:00 AM | 15m | ☕ BREAK
11:00 AM–12:30 PM | 1.5 hrs | Topic 2 — ProM & Scale Center Migration & EOL | Kent, Ravi | Align on 12-month LRP and recommendations for migrating ProM and Scale Center customers to Scale360, including staffing, feature timelines, and EOL dates. | Scale360, Scale Center, ProM | 12-Month LRP findings doc (Kent/Ravi)
12:30–1:30 PM | 1 hr | 🍽 LUNCH
1:30–2:30 PM | 1 hr | Topic 4 — Internal Support / CSM | Ravi, Kent | Proposal for the Scale360 internal product experience for internal users and CSMs, drawing on Scale Center and ProM learnings. | Scale360 | Proposed internal user experience doc (Ravi/Kent)
2:30–3:30 PM | 1 hr | Topic 5 — Product Launch to GA | Ravi | Confirm what is in scope for Dreamforce Sep 15. Align on committed vs. stretch deliverables. Outline of product launch plan and what it takes to GA a product. Assign engineering work and ownership across multiple work streams (security legal etc). | Scale360 | DF scope doc; GTM Launch Hub work streams outline (Ravi)
3:30–3:45 PM | 15m | ☕ BREAK
3:45–5:15 PM | 1.5 hrs | Topic 10 — Architecture Comparison | Auro, Paymon | Current architecture vs. new architecture comparison. Helpful for migration and EOL discussions. MCP Servers & Platform Infrastructure. | Scale360 | Architecture comparison deck (Auro/Paymon)
5:15–5:30 PM | 15m | Day 2 Recap & Action Items | Betty | Capture all open items. Confirm decisions made. Preview Day 3 agenda. | Scale360

## Day 3
Time | Duration | Title/Topic | Facilitator/Owner | Description/Goals | Product Tags | Links/Artifacts
8:30–8:45 AM | 15m | Day 3 Kickoff | Laksh, Betty | Open items from Day 2, priorities for today. | Scale360 | No artifacts required
8:45–10:15 AM | 1.5 hrs | Breakout - Scale360 Elevator Pitch | TBD | Develop and refine the Scale360 elevator pitch for stakeholder communications and executive briefings. | Scale360 | Elevator pitch template
10:15–11:15 AM | 1 hr | Workshop Outcomes Review & Key Decisions w/ Pending Decision Log | Betty | Review and finalize workshop outcomes: Product Strategy & Alignment, R266 Deliverable Roadmap and Agentforce Claude work allocation. | Scale360 | No artifacts required
11:15 AM–12:45 PM | 1.5 hrs | Workstream Planning & Action Items | Betty | Review workstream status and commitments across P1–P6. Confirm engineering ownership sprint assignments and delivery targets for R266. Comprehensive action item table: owner action due date. No action without a named owner. Confirm async follow-ups for items not closed in session. | Scale360 | No artifacts required
12:45–1:15 PM | 30m | Close & Next Steps | Betty | Summarize all decisions made across 3 days. Confirm next sync cadence. Betty to publish action item table and updated workstream tracker by EOD+1. | Scale360 | No artifacts required

## Topics
Topic | Duration | Title/Topic | Facilitator/Owner | Description/Goals | Product Tags | Additional Notes
Topic 1 - Headless Experience |  | Headless Experience (Scale360, Scale Center, ProM) | Kent, Mayuresh | Overview and description of product scope. Prioritized use cases for entire Headless portfolio (ProM, Scale360, etc) | Scale360, Scale Center, ProM | Additional Participation: Mayuresh Verma
Topic 1 - Headless Experience |  | Headless Experience - Automation & Proactive Delivery | Samir | What would we automate for the user and what would be proactive | Scale360, Scale Center, ProM | Additional Participation: Sri Dinavahi
Topic 1 - Headless Experience |  | Headless Experience - MCP Servers & Platform Infrastructure | Paymon | MCP Servers & Platform Infrastructure | Scale360, Scale Center, ProM | Additional Participation: Sri Dinavahi
Topic 1.1 - In-App Experience |  | In-App Experience (Scale360) | Samir | What would we automate for the user and what could be done proactively | Scale360 | Additional Participation: Sri Dinavahi Dan Donovan
Topic 2 - ProM & SC Migration & EOL |  | ProM & Scale Center Parity & EOL / Migration to Scale360 | Kent, Auro, Laurent | Recommendation on how we should approach Scale360 migration | Scale360, Scale Center, ProM | Type: Discuss, Decide; Outcomes: Alignment on path forward migration plan; Additional Participation: Sri Dinavahi
Topic 3 - Basic & Elite Scale360 |  | Basic & Elite Scale360 Product | Ravi, Kent | Tier definitions, go-to-market strategy | Scale360 | Outcomes: Definition of Elite; Additional Participation: Sri
Topic 4 - Internal Support / CSM |  | Internal Support / CSM | Ravi, Kent | Internal experience for Customer Success Managers and support teams | Scale360 | Additional Participation: Sri
Topic 5 - Product Launch to GA |  | Product Launch to GA | Ravi | Operational readiness & product launch checklist (200+ items) | Scale360
Topic 6 - Pricing & CTS |  | Pricing & CTS Opt-In AI-Based - Agentforce vs Claude | Paymon | Agentforce vs. Claude | Scale360 | Additional Participation: Sri
Topic 6 - Pricing & CTS |  | Pricing & CTS Opt-In AI-Based - Opt-in Strategy |  | Opt-in: experience for customers who haven't opted in; AI-based strategy | Scale360 | Type: Decision; Outcomes: POV on customer experience
Topic 6 - Pricing & CTS |  | Pricing & CTS Opt-In AI-Based - Pricing | Ravi | Pricing & CTS | Scale360
Topic 7 - RCA Agent |  | RCA (Root Cause Analysis Agent) | Ravi | Exit criteria for pilot | Scale360 | Covers: skill-based vs. hardcoded RCA LLM gateway vs. Agentforce RCA + Scale Insight unified flow Java/Python ReAct loop
Topic 8 - Alerting & Enrichment |  | Alerting & Alert Enrichment - Enrichment Plan | Laurent, Paymon | Plan for getting enrichment for Scale360 platform | Scale360 | Covers: alerting events platform alert onboarding (15 metrics) UI access gates Slack notifications cohort org rollout
Topic 8 - Alerting & Enrichment |  | Alerting & Alert Enrichment - Events Platform | Laurent, Paymon | Additional enrichment from Events platform and what's possible | Scale360
Topic 8 - Alerting & Enrichment |  | Alerting & Alert Enrichment - Migration Tools | Laurent, Paymon | Tools to migrate current Argus to Events | Scale360
Topic 8 - Alerting Seeds |  | Alert onboarding seed |  |  | Scale360 | Seed: Alert onboarding (15 metrics): status for 264 what remains for 266?
Topic 8 - Alerting Seeds |  | Alerting enrichment events platform seed |  |  | Scale360 | Seed: Alerting enrichment events platform: collaboration between Malik Plash Shree — handoff and 266 plan
Topic 8 - Alerting Seeds |  | Warden AI Ops auto-remediation seed |  |  | Scale360 | Seed: Warden AI Ops auto-remediation: callback TD from MonCloud — 266 dependency plan
Topic 8 - Alerting Seeds |  | Alert rollout seed |  |  | Scale360 | Seed: Alert rollout: cohort org access gates UI testing broader rollout timeline
Topic 9 - Multi-Org |  | Multi-Org | Paymon |  | Scale360 | Covers: multi-org support org-level alerting cross-org insights tenant isolation
Topic 9 - Multi-Org Seeds |  | Multi-org alerting seed |  |  | Scale360 | Seed: Multi-org alerting: scope for 266 — which alert types which tenant tiers?
Topic 9 - Multi-Org Seeds |  | Org throttling seed |  |  | Scale360 | Seed: Org throttling and governor limit cases across orgs
Topic 9 - Multi-Org Seeds |  | Scale Center multi-org data model seed |  |  | Scale360 | Seed: Scale Center multi-org data model: right architecture going into 266?
Topic 10 - Multi-Cloud |  | Multi-Cloud | Paymon |  | Scale360 | Covers: multi-cloud support G2H parity commercial vs. G2H alerting Monitoring Cloud dependency
Topic 10 - Multi-Cloud Seeds |  | Multi-cloud spike results seed |  |  | Scale360 | Seed: Multi-cloud spike results (Malik) — what did we learn what's the 266 plan?
Topic 10 - Multi-Cloud Seeds |  | G2H parity seed |  |  | Scale360 | Seed: G2H parity with commercial alerting on events platform — timeline (Q3 vs Q4)
Topic 10 - Multi-Cloud Seeds |  | 50000 tenant support seed |  |  | Scale360 | Seed: 50000 tenant support target: what does engineering need to deliver?
Topic 10 - Multi-Cloud Seeds |  | UIP Heron seed |  |  | Scale360 | Seed: UIP Heron as Splunk alternative: spike status outstanding questions for 266
Cross-Cutting Seeds |  | 3X productivity seed |  |  |  | Seed: 3X productivity: what did we learn what stays what changes for 266?
Cross-Cutting Seeds |  | Blocker escalation seed |  |  |  | Seed: Blocker escalation: define the process so dependencies don't sit unresolved for weeks
Cross-Cutting Seeds |  | Pre-Work Before India seed |  |  |  | Seed: Pre-Work Before India (Late June – Early July)

## Decision Log
Decision | Owner | Options | Status | Notes
D2: AgentForce vs. Claude AI backend | Karishma | Options: AgentForce / Claude / Hybrid | Status: TBD | Decision number: D2
D3: 264 Pilot Scope Lock | Karishma, Kent | Options: Full feature set vs. MVP | Status: TBD | Decision number: D3
D4: ProM EOL Date | Karishma, Sri | Options: Feb 2027 / Later | Status: TBD | Decision number: D4
D5: Sprint 9A Hardening Lock | Laksh, Archana | Options: Hardening-only vs. features allowed | Status: TBD | Decision number: D5
D6: NGA Accuracy Threshold | Karishma, Kent | Defines migration gate criteria | Status: TBD | Decision number: D6
D7: LLM Token Tracking Scope | Paymon, Karishma | Per-RCA instrumentation scope | Status: TBD | Decision number: D7

## Pre-Work
Item | Owner | Target Date | Notes
Finalize PM artifacts and topic owners in release planning doc | Kent, Ravi, Betty | Target: Jul 2 (past)
Demo to Sri and team feedback session | Karishma, Laksh, All team | Target: Jul 6 (past)
Consult Sri for inputs + assign team responsibilities | Betty, Sri | Target: Jul 7 (past)
Add topics to feature sections in planning doc | All team | Target: Jul 10 (urgent) - Bold/highlighted
Schedule strategy review with Donovan + Karishma before Hyderabad trip | Samir | Target: Before Jul 22
Dreamforce, pilot and 264/266 product scope alignment | Karishma, Kent, Ravi | Target: Before Jul 22
Coordinate with Tara to reserve meeting rooms for 3-day sessions | Betty | Target: Before Jul 22
Block Shri calendar for relevant product strategy sessions (Wed + Thu) | Betty | Target: Before Jul 22
Finalized agenda published | Betty | Target: Jul 15
Prepare workshop artifacts — architectural and strategic topic documentation | Kent, Ravi | Target: Jul 15
12-month LRP roadmap document for ProM/Scale Center → Scale360 migration | Kent, Ravi, Auro | Target: Before Jul 22

## People & RACI
Name | Role | Responsibilities | Sessions | Notes
Betty Yip | Betty | TPM — Scale360 | Person code: Betty
Karishma Lalwani | Karishma | PM — Scalability Products | Person code: Karishma
Kent Allison | Kent | PM — Scale360 & ProM | Person code: Kent
Ravi Raina | Ravi | PM — Scale360 & Scale Center | Person code: Ravi
Samir Damle | Samir | UI/UX | Person code: Samir
Laksh Venka | Laksh | Engineering Lead | Person code: Laksh
Paymon Teyer | Paymon | Lead Architect / PO | Person code: Paymon
Laurent Pautet | Laurent | Lead Architect | Person code: Laurent
Archana Sethuraman | Archana | Engineering Manager | Person code: Archana
Sriram Dinavahi | Sri | SVP Engineering — Exec Sponsor | Person code: Sri
R - Responsible |  | Leads / runs the session
A - Accountable |  | Decision authority; owns the outcome
C - Consulted |  | Must contribute input before decisions
I - Informed |  | Present or updated after session
Betty Yip | Betty Yip | Sessions: 1.1, 1.4, 1.5, 1.7, 2.1, 2.7*, 2.8, 2.9, 3.1*, 3.2, 3.4, 3.5, 3.6, 3.7, 3.8, 3.9 (Total: ~6.5 hrs) |  | Sessions Responsible For
Karishma Lalwani | Karishma Lalwani | Sessions: 1.2, 1.3 (Total: ~2.25 hrs) |  | Sessions Responsible For
Kent Allison | Kent Allison | Sessions: 1.6 (Total: ~0.75 hrs) |  | Sessions Responsible For
Laurent Pautet | Laurent Pautet | Sessions: 2.2, 2.3 (Total: ~1.5 hrs) |  | Sessions Responsible For
Paymon Teyer | Paymon Teyer | Sessions: 2.4, 2.5 (Total: ~1.5 hrs) |  | Sessions Responsible For
Archana Sethuraman | Archana Sethuraman | Sessions: 3.3 (Total: ~0.75 hrs) |  | Sessions Responsible For

## Header Metadata
Field | Value | Notes
Event Info | Scale360 R266 Strategic Planning - India Offsite | Badge: DRAFT
Event Info | Jul 22–24 2026 · Salesforce Hyderabad + Google Meet
Event Info | 8:30 AM – 5:00 PM IST
Event Info | TPM: Betty Yip
Event Info | Agenda and Artifacts deadline: Jul 20 2026
Event Info | Topics deadline: Jul 10 2026